**Release and Sprint Plans**

**Team Number**

|  |  |
| --- | --- |
| Student Number | Team Member Name |
| N9431594 | Justin Lillico |
| N9830642 | Teo Kok Fuh |
| N8637156 | Kevin Taing |
| N8855650 | Andy Nguyen |
| N9937072 | Dennis Tran |
|  |  |

Tutor: Jesse St.Germain

Version:1

Date:17/08/17

**Table of Contents**

[Release Plan 1](#_Toc426554714)

[Release 1 1](#_Toc426554715)

[Feature Title 1 1](#_Toc426554716)

[Feature Title 2 1](#_Toc426554717)

[Release 2 1](#_Toc426554718)

[Feature Title 1 1](#_Toc426554719)

[Feature Title 2 1](#_Toc426554720)

[Release 3 2](#_Toc426554721)

[Feature Title 1 2](#_Toc426554722)

[Feature Title 2 2](#_Toc426554723)

[Delivery Schedule 2](#_Toc426554724)

[Estimated Velocity: 2](#_Toc426554725)

[Sprint Plan 3](#_Toc426554726)

[Sprint 1 3](#_Toc426554727)

[Current Velocity: 3](#_Toc426554728)

[Story ID: Title 3](#_Toc426554729)

[Story ID: Title 3](#_Toc426554730)

[Story ID: Title 3](#_Toc426554731)

Release Plan

# Release 1

Delivery date: 25th October 2017 Total Story Points:35

For the first release, a working prototype of the smart city system will be created. The system will enable users a way to log-in and create an account for use with the system. Smart City will provide information about the Brisbane city. Users will be able to view said information in a map feature and view less relevant information should they desire.

## Landing Page

Users can view the features of the system and sign on.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| S05 | Welcome page | 1 |
| S01 | Log-in process | 1 |
| S02 | Registration process | 2 |
| S19 | Log-out process | 1 |
|  | Story Point Sub-Total: | 5 |

## Administrator Account

Admins can log-in and access the admin specific tools.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| S06 | Admin account setup page | 4 |
| S09 | Data manipulation | 4 |
| S10 | Admin account creation | 2 |
|  | Story Point Sub-Total: | 10 |

## User Account

Users can select their account type and view map features

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| S12 | Generic city information | 2 |
| S15 | Tourist account | 1 |
| S16 | Student account | 1 |
| S17 | Business account | 1 |
|  | Story Point Sub-Total: | 5 |

## System Features

The system will provide the users with relevant information

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| S11 | Segmented data | 1 |
| S14 | Map updates | 8 |
| S18 | System Scalability | 4 |
| S13 | Map data | 2 |
|  | Story Point Sub-Total: | 15 |

# Release 2

Delivery date: To be announced Total Story Points:36

Provide users with advanced functionality for finding and reviewing locations. The system will also allow users to search for destinations outside of Brisbane including Sydney, Melbourne, Adelaide, etc. Alongside these new functions the system will also expand so that additional city information can be inserted such as bus services and health services.

## User Enhancements

Provide users of the system with additional services and tools so that information can be tailored more accurately and accounts can be secured.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| S03 | Viewing additional information | 8 |
| S07 | Account security | 2 |
| S08 | Account recovery | 2 |
|  | Story Point Sub-Total: | 12 |

## Location Services

This will provide users with more accurate information regarding locations.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| S22 | Search function | 4 |
| S28 | Rating review system | 4 |
| S30 | Live weather updates | 8 |
|  | Story Point Sub-Total: | 16 |

## Communication Features

Users will be able have contact with support services and be able to integrate the service with their social media

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| S24 | Contact Us Page | 2 |
| S25 | FAQ page | 1 |
| S26 | Social Media Integration | 1 |
| S29 | Online Forum | 4 |
|  | Story Point Sub-Total: | 8 |

# Release 3

Delivery date: To Total Story Points:16

Mobile functionally will be introduced to further support the system to increase functionality. To enhance the service an ability to change the language will be incorporated.

## Language Change

Users will be able to change the language into their preferred language.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| S23 | Language Change | 8 |
|  | Story Point Sub-Total: | 8 |

## Mobile Compatibility

To increase accessibility the service shall support a mobile compatible version.

|  |  |  |
| --- | --- | --- |
| Story ID | Story Title | Story Points |
| S27 | Mobile-ready Version | 8 |
|  | Story Point Sub-Total: | 8 |

# Delivery Schedule

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 |
| Sprint 1 | | | | Sprint 2 | | | |
| Release 1 | | | | | | | | |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Week 14 |  | Week 15 |  |  |  |  |  |
| Sprint 3 | | | |  | |  | |
| Release 3, 4, … | | | | | | | |

## Estimated Velocity:

Sprint Plan

# Sprint 1

Total Story Points: Total Hours:

## Current Velocity:

## Story ID: Title

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  | Story Points: Total Hours: |  |  |

## Story ID: Title

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  | Story Points: Total Hours: |  |  |

## Story ID: Title

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  | Story Points: Total Hours: |  |  |