## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 119 | 119
1 | 89 | 93
2 | 57 | 65
3 | 24
4 | 0 | 0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 36 | 36
19 | 34 | 35
18 | 32 | 30
17 | 30 | 30 | Sprint 1
16 | 28 | 26 | Issues:
15 | 26 | 25 | User story 13: Map data
14 | 24 | 23 | T25: Creating data points for each location
13 | 22 | 22
12 | 20 | 22 | User story 12: Account information
11 | 18 | 20 | T19: Displaying the relevant info to each user
10 | 16 | 20
9 | 14 | 17 | User story 2: Account registration
8 | 12 | 15 | T36: Form validation
7 | 10 | 8
6 | 8 | 6
5 | 6 | 5 | Did not complete:
4 | 4 | 5
3 | 2 | 5 | T19 - Exclude certain information
2 | 0 | 5 | T30 - Code admin to add/ modify city data
1 | 0 | 4 | T31 - Creating overlay for map tools
0 | 0 | 3
Sprint 2
Adaptation:
Moved user story 22: search
Sprint 2 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 55 | 55 | Issues:
19 | 52 | 50 | User story 18: System scalability
18 | 48 | 50 | T36 - Creating additional cities
17 | 45 | 50
16 | 43 | 48 | User story 22: Search
15 | 40 | 44 | T43 - Displaying correct search results
14 | 35 | 44
13 | 30 | 40
12 | 27 | 35
11 | 25 | 35
10 | 20 | 30
9 | 18 | 25
8 | 16 | 22
7 | 14 | 22
6 | 12 | 18
5 | 10 | 12
4 | 8 | 10
3 | 6 | 9
2 | 4 | 0
1 | 2 | 0
0 | 0 | 0